## Sheet1
Estimation Milestone 3
· Complete estimation record using the following techniques: Analogy, Decomposition, Fibonacci Numbers, while covering three dimensions: Size, Effort, Schedule
Estimation Record
|  |  | Size Measure | Typical Effort per Size Measure ( person/ hours) | Size | Expert A Expert B Effort (Person/Hours) |  | Final ( Fibonacci)
| Requirements | Definition of users( personas) | # roles | 0.2 | 5 | 1 | 1 | 1
|  | Definition of Scope and Limitations | # attributes | 0.1 | 10 | 1 | 1 | 2
|  | Engineering Requirements List | # requirements | 0.4 | 5 | 2 | 1 | 3
| Config Management | Config items list | #CI items | 0.09 | 11 | 1 | 1 | 2
| Estimation | Estimation Record | #activities | 0.09 | 13 | 1 | 1 | 1
| Design | State Transition Diagram | #states | 0.25 | 4 | 1 | 0.5 | 2
|  | Definition of usecases | #use cases | 0.5 | 4 | 2 | 2 | 2
|  | Definition of Fields | #fields | 0.2 | 20 | 4 | 2 | 2
|  | Definition of Reports | #reports | 1 | 2 | 2 | 2 | 3
| Peer reviews | Issues from peer reviews retained | # issues | 0.2 | 25 | 5 | 4 | 5
| Implementation | Defect tracking system | # user screens | 6 | 1 | 6 | 8 | 8
| Test Design | Test Cases | # test cases | 0.33 | 6 | 2 | 2 | 2
| Test Execution | Defects from testing recorded | # test cases | 0.33 | 6 | 2 | 2 | 2
| Total | [6 empty] | 35
Note on C6: Author: Decomposition
Note on F6: Author: Analogy